## Slide 1
Stakeholder Engagement
during Implementation of
Universal MSI Screening
in a Large Healthcare System

## Slide 2
1. Determine engagement objectives
3. Develop plan for engagement
4. Implement plan
5. Evaluate effectiveness of implementation
6. Revise based on stakeholder feedback
2. Identify stakeholders

## Slide 3
1. Determine engagement objectives
Universal Lynch syndrome screening is the objective
Questions to consider:
In all colon cancer patients?
In all endometrial cancer patients?
Newly diagnosed only?
At all facilities?
IHC vs. MSI vs. both?
Cost/benefit analysis
Having a clear objective helps:
Clarify the goal for the team
Identify who to include in the plan
Clarify what is needed to implement the plan
Determine when and how to make this routine

## Slide 4
2. Identify stakeholders
What is a Stakeholder?
A person, group or organization, that has interest or concern in an organization.
Stakeholders can affect or be affected by the organization's actions, objectives, and policies.
There is a wide variety of possible stakeholders: | 
Oncology | Primary care (Internal Medicine/Family Practice, NP)
Gastroenterology | Genetics (Medical Geneticist, Genetic Counselor)
Physician groups | Laboratory (laboratory director, laboratory staff)
Organizational leadership | Pathology (histology technicians, pathologists, pathology director)
Gynecology | Surgery (surgeons, surgical technicians, surgical nurses)
Dermatology | Clinical lab services team (analytic support team)
Informatics (informatics director) | Business services (cost and billing issues)

## Slide 5
3. Develop plan for engagement
Inform
Consult
Seek targeted feedback on what is working well, what is needed, and what can be done differently. Eliminate overlap.
Work directly with staff to ensure their concerns and ideas are understood and considered throughout the process. Encourage feedback to voice concerns about process.
Place final decision-making in the hands
of impacted staff when possible.
Provide relevant information to stakeholders about the benefits and opportunities of universal screening at the right level. Engage stakeholders early. Re-educate involved staff.
Involve
Partner with impacted staff on the actual decision process, including identifying alternatives and solutions.
Collaborate
Empower
Different stakeholders can be engaged in different ways based on their role

## Slide 6
4. Implement plan
Who will be in charge of implementing the plan?
When will implementation happen? Consider:
  Getting time at pre-existing meetings
  Offering multiple opportunities for stakeholders to attend
  Having a way for stakeholders to get information if they miss a meeting
What methods will you use? Consider:
  Handouts
  Meetings
  Presentations
Who do you need involved to ensure that all stakeholders are ‘at the table’?
How will you evaluate the effectiveness?

## Slide 7
5. Evaluate effectiveness of implementation
Stakeholder satisfaction and buy-in
Allow for opportunities to build relationships and celebrate successes.
Provide periodic updates on progress.
Ask stakeholders regularly, if things are going well.

## Slide 8
6. Revise based on stakeholder feedback
Make changes if things aren’t going smoothly
Report back to stakeholders about changes made
Create an easy way for stakeholders to provide ongoing feedback